## Slide 1: Event Planning Valentine’s Day Carnation Sale
November 29, 2018

## Slide 2: First Event, Valentine’s Day Carnation Flower Sale Due: Thursday, February 14, 2019
Objective: To sell a minimum of 12 carnations per student prior to Valentine’s Day.
Keep in mind: There is 133 students in the Spanish Club.

## Slide 3: Event Leader
Creates an inspiring vision.
Motivates and inspires people to engage with that vision.
Manages delivery of that vision.
Carnation Event Leader: Rubi Gutierrez

## Slide 4: Event Workflow-Tasks to be done & by Who?
-Find how much are the carnations in bulk (1600)-Sandra, Joram, Adonay
Details about flower (pink, white, and red)
How quick is shipping
Return policy
-Gain feedback from Spanish Club members on sale- Daniel, Carlos
-Find how much are the cards to go with the carnations (1600)- Jackie
-Decide who is going to deliver the carnations during 3rd block.-Joram, Rubi
-speak to AgriScience teacher to see if she can hold.-Joanna Colchado

## Slide 5: Event Timeline
All information gathered by 12/12/19
Next meeting 12/12/19
Order to be submitted early Jan.2019
Start selling carnation cards on 1/21/19-until 2/8/19
Receive flowers the day before Valentine’s Day
Deliver carnations during 3rd block on Valentine’s Day

## Slide 6: Assigning of tasks to other subgroups
Advertising and Photos
-Announcement (Mon and Wed from 1/21-2/8)
-Publish on Webpage
-Posters around the school (2 per hall)
-Google Slide for Cafeteria
-Social Media (SnapChat, Instagram, Twitter)

## Slide 7: Event Budget with estimated cost per item & total cost
To be completed by Sandra, Joram, Adonay

## Slide 8: Who is likely to participate in this event?
Teachers
Students
Parents

## Slide 9: Risks of event and plans to mitigate identified risks
-Flowers do not arrive on time.Use US vendor only and emphasize the importance of arriving on time the day before Valentine.
-Enough cards to sell. Sell on Valentine’s Day at the caf.
-Collect cards same day they sell with money.
-Broken flowers, buy 5% extra, and if they are not broken, sell the remaining in the cafeteria.
-To avoid flowers from dying overnight, speak to AgriScience teacher to see if she can hold.

## Slide 10: How will the event be evaluated?
-Gain feedback from Spanish Club members via Google Form link about the sale.

## Slide 11: Our Next Meeting
Wednesday
12/12/18
@ 3:15-4:30